## Adrian Angeles
To-do list
To be completed by: |  |  |  | Name: Adrian Angeles
Deadline: |  |  |  | Date: 10/26/25
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Initial Meeting | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1 Day | Brought up Ideas for how to Structure Project throughout froup
100% | Preparation | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1 Day | SQL Noir Review
100% | Mystery Outline | 2025-10-22 | 2025-10-22 | 2025-10-22 | 1 Days | Brainstormed ideas for creation of Mysteries
100% | Query + MD Creation | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2 Day | Created Notebook In Azure Data Studios
100% | Feedback Session | 2025-10-25 | 2025-10-25 | 2025-10-25 | 1 Day | Provided Feedback on Peers work
100% | Pair Recording Session | 2025-10-26 | 2025-10-26 | 2025-10-26 | 1 Day | Recorded with Ali and handed over individual recordings and nnotebook
100% | Chart Finalization | 2025-10-26 | 2025-10-26 | 2025-10-26 | 1 Day | Finalized the Charts

## Aditya Dwivedi
To-do list
To be completed by: |  |  |  | Name: Aditya Dwivedi
Deadline: |  |  |  | Date: 10/26
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Initial Meeting | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1Day | Suggested which software should be used for notebook creation
75% | Preparation | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1 Day | Went Over Task Requirements and gave suggestions for following it to the group
100% | Mystery Creation | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1Day | Created Mysteries according to assignment requirements
100% | Query Creation + MD Creation | 2025-10-22 | 2025-10-23 | 2025-10-23 | 1DDay | Created both markdown and body portion of queries
100% | Feedback Session | 2025-10-25 | 2025-10-25 | 2025-10-25 | 1D | Provided feedback for how files should be shared between group
100% | Pair Recording Session | 2025-10-25 | 2025-10-25 | 2025-10-26 | 1D | Recorded with Mret
100% | Combine Videos | 2025-10-26 | 2025-10-26 | 2025-10-26 | 1D | Stitched together Group Videos
100% | GitHub Upload | 2025-10-26 | 2025-10-26 | 2025-10-26 | 1Day | Uploaded Stitched vVdeo

## Ali Mustafa
To-do list
To be completed by: |  |  |  | Name: Ali Mustafa
Deadline: |  |  |  | Date: 10/26
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Initial Meeting | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1 Day | Set up Meeting
100% | Preparation | 2025-10-22 | 2025-10-22 | 2025-10-22 | 1 Day | Reviewed Previous Chapters for ideas
100% | Mystery Creation | 2025-10-22 | 2025-10-22 | 2025-10-22 | 1 Day | Craeted Mysteries
100% | Query Creation | 2025-10-23 | 2025-10-23 | 2025-10-23 | 1 D | Created Follow up Queries
100% | Markdown Creation | 2025-10-24 | 2025-10-24 | 2025-10-24 | 1Day | Finalized Markdown
100% | Feedback Session | 2025-10-25 | 2025-10-25 | 2025-10-25 | 1Day | Gave feedback for how group can improve on file formatting
100% | Pair Recording | 2025-10-25 | 2025-10-25 | 2025-10-17 | 1Day | Recorded with Adrian
100% | Submission | 2025-10-26 | 2025-10-26 | 2025-10-26 | 1Day | Submitted Assignment

## Mret Hein
To-do list
To be completed by: |  |  |  | Name: Mret Hein
Deadline: |  |  |  | Date: 10/26
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Initial Meeting | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1 Day | Provided Databases to choose from for Group Synergy
100% | Preparation | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1 Day | Helped finalize which database would be used
100% | Mystery Creation | 2025-10-23 | 2025-10-23 | 2025-10-23 | 1Day | Created Mysteries and tested for SQL Compatibility
100% | Query Creation | 2025-10-23 | 2025-10-23 | 2025-10-23 | 1Day | Created Queries and troubleshooted other members queries
100% | Markdown Creation | 2025-10-23 | 2025-10-23 | 2025-10-23 | 1Day | Created Markdown for Notebook
100% | Feedback Session | 2025-10-25 | 2025-10-25 | 2025-10-25 | 1Day | Provided Feedback o n structure of Group members notebooks
100% | Pair Recording | 2025-10-25 | 2025-10-25 | 2025-10-25 | 1Day | Recorded with Ali